## Gantt Chart
Bright Coffee Shop — Project Gantt Chart
BrightLearn Case Study 1 ¦ Due: 31 March 2026 ¦ 149,115 transactions analysed
Task | Status | Mar 24 W1 | Mar 25 W2 | Mar 26 W3 | Mar 27 W4 | Mar 28 W5 | Mar 29 W6 | Mar 30 W7 | Mar 31 W8
TASK 1 — PLANNING & ARCHITECTURE (MIRO)
Design data flow & architecture diagram | Done
List key insights to deliver | Done
Outline calculations to perform | Done
TASK 2 — DATA PROCESSING IN DATABRICKS
Convert Excel/data to CSV | Done
Load CSV into Databricks (Extract) | Done
Transform: fix unit_price, total_amount | In Progress
Create transaction_time_bucket column | In Progress
SQL GROUP BY queries (Gold layer) | Pending
TASK 3 — DATA ANALYSIS IN EXCEL
Export Gold tables to Excel / CSV | Pending
Build pivot tables & charts | Pending
Revenue, peak times, top products | Pending
TASK 4 — CEO PRESENTATION
Write methodology document | Pending
Build PowerPoint presentation | Pending
Add recommendations & next steps | Pending
Final review & GitHub submission | Pending | [7 empty] | ★ DUE
LEGEND
Task 1 — Planning & architecture
Task 2 — Data processing (Databricks)
Task 3 — Excel analysis
Task 4 — CEO presentation
★ Deadline — 31 March 2026